## 표지
WBS 진척율 관리 V 1.0
통합연구지원시스템 화상평가 및 통계∙분석 서비스 구축
업무명 : 사업관리
2020. 09. 01.
관리본문서 | 관리본
문서관리번호 | NB-PT-010
작 성 자 | 김수혜
보안등급 | 대 외 비

## 총괄표
공정 |  | 중요도 | 금주실적 (42주차) |  |  |  | 차주계획 | 비고
|  |  | 누적계획 | 누적계획 (차주) | 누적실적 | 달성율
전체 |  | 100% | #REF! | #REF! | #REF! | #REF! | #REF!
사업관리 |  | 18% | 99.08% | 100% | #REF! | #REF! | 100%
시스템공통 | 소계 | 10% | #REF! | #REF! | #REF! | #REF! | #REF!
| 분석 | 18% | #REF! | #REF! | #REF! | #REF! | #REF!
| 설계 | 22% | #REF! | #REF! | #REF! | #REF! | #REF!
| 구현 | 30% | #REF! | #REF! | #REF! | #REF! | #REF!
| 시험 | 23% | #REF! | #REF! | #REF! | #REF! | #REF!
| 전개 | 7% | #REF! | #REF! | #REF! | #REF! | #REF!
UI공통 | 소계 | 11% | #REF! | #REF! | #REF! | #REF! | #REF!
| 분석 | 18% | #REF! | #REF! | #REF! | #REF! | #REF!
| 설계 | 30% | #REF! | #REF! | #REF! | #REF! | #REF!
| 구현 | 40% | #REF! | #REF! | #REF! | #REF! | #REF!
| 전개 | 12% | #REF! | #REF! | #REF! | #REF! | #REF!
평가 및 교류협력 | 소계 | 44% | 39.07% | 39.8% | #REF! | #REF! | 39.8%
| 분석 | 18% | 40% | 40% | #REF! | #REF! | 40%
| 설계 | 22% | 30% | 30% | #REF! | #REF! | 30%
| 구현 | 30% | 5% | 5% | #REF! | #REF! | 5%
| 시험 | 23% | 90% | 90% | #REF! | #REF! | 90%
| 전개 | 7% | 89.5% | 100% | #REF! | #REF! | 100%
빅데이터시각화 | 소계 | 17% | #REF! | #REF! | #REF! | #REF! | #REF!
| 분석 | 18% | #REF! | #REF! | #REF! | #REF! | #REF!
| 설계 | 22% | #REF! | #REF! | #REF! | #REF! | #REF!
| 구현 | 30% | #REF! | #REF! | #REF! | #REF! | #REF!
| 시험 | 23% | #REF! | #REF! | #REF! | #REF! | #REF!
| 전개 | 7% | #REF! | #REF! | #REF! | #REF! | #REF!

## WBS진척율
업무명 | 가중치 | 진척율 | 국가균형발전종합정보시스템 2단계 구축
|  |  | 2020년 | [18 empty] | 2021년
|  |  | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차
|  |  | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차
|  |  | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일
총괄 | 100% | 계획 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 실적 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 달성율 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
사업관리 | 18% | 계획 | 0.621% | 5.492% | 8.893% | 13.49% | 17.83% | 24.01% | 25.74% | 26.36% | 28.78% | 33.6% | 36.21% | 38.98% | 40.1% | 40.87% | 41.5% | 44.01% | 47.36% | 49.45% | 54.27% | 60.58% | 62.7% | 64.37% | 66.34% | 67.56% | 71.88% | 72.5% | 73.12% | 73.74% | 75.35% | 75.97% | 76.59% | 77.21% | 78.82% | 79.44% | 80.91% | 83.49% | 86.3% | 86.92% | 89.29% | 92.16% | 93.28% | 99.08% | 100%
|  | 실적 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 달성율 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
시스템공통 | 11% | 계획 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 실적 | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 달성율 | 0% | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
UI공통 | 10% | 계획 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 실적 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 달성율 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
평가및교류협력 | 44% | 계획 | 0% | 0% | 0% | 0% | 0% | 1% | 2% | 3% | 4% | 4% | 4% | 4% | 4% | 4.396% | 5.188% | 5.98% | 6.772% | 7.96% | 8.752% | 10.6% | 10.68% | 10.75% | 10.83% | 10.9% | 11.05% | 11.2% | 11.35% | 11.5% | 11.65% | 11.8% | 11.95% | 12.1% | 12.1% | 12.1% | 14.86% | 21.3% | 25.32% | 30.31% | 36.78% | 37.89% | 38.33% | 39.07% | 39.8%
|  | 실적 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 달성율 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
빅데이터시각화 | 17% | 계획 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 실적 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
|  | 달성율 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!

## 진척율기준
WBS 작성기준
1. 요구정의, 분석, 설계, 구현, 시험, 이행 가중치는 기능점수 산출기준의 가중치를 근거로 적용
2. 각 공정별 가중치는 수행 프로젝트 경험치를 기준으로 산정
3. 진척율 100%(완료)는 공정에 해당하는 산출물 작성 완료 및 PL, PM 검토완료를 의미
※ 산물출 고객 검토는 PM 검토 완료 후 PM또는 PL이 고객검토 요청
4. 단계별 완료 시 산출물 품질점검 실시 후 단계별산출물 일괄 제출

## 사업관리(계획)
공정명 | 중요도 |  |  | 시작예정일 | 종료예정일 | 업무담당 | 2020년 | [18 empty] | 2021년 | [23 empty] | 2020년 | [18 empty] | 2021년 | [23 empty] | 산출물
[7 empty] | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차 | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차
[7 empty] | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차 | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차
| Stage | Step | Task |  |  |  | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일 | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일
사업관리 | [6 empty] | 2020년 1주차 8월4주차 8월21일: 0.621%; 2020년 2주차 8월5주차 8월28일: 5.492%; 2020년 3주차 9월1주차 9월4일: 8.893%; 2020년 4주차 9월2주차 9월11일: 13.49%; 2020년 5주차 9월3주차 9월18일: 17.83%; 2020년 6주차 9월4주차 9월25일: 24.01%; 2020년 7주차 10월1주차 10월2일: 25.74%; 2020년 8주차 10월2주차 10월9일: 26.36%; 2020년 9주차 10월3주차 10월 16일: 28.78%; 2020년 10주차 10월4주차 10월 23일: 33.6%; 2020년 11주차 10월5주차 10월30일: 36.21%; 2020년 12주차 11월1주차 11월6일: 38.98%; 2020년 13주차 11월2주차 11월13일: 40.1%; 2020년 14주차 11월3주차 11월 20일: 40.87%; 2020년 15주차 11월4주차 11월27일: 41.5%; 2020년 16주차 12월1주차 12월4일: 44.01%; 2020년 17주차 12월2주차 12월11일: 47.36%; 2020년 18주차 12월3주차 12월18일: 49.45%; 2020년 19주차 12월4주차 12월25일: 54.27%; 2021년 20주차 1월1주차 1월1일: 60.58%; 2021년 21주차 1월2주차 1월8일: 62.7%; 2021년 22주차 1월3주차 1월15일: 64.37%; 2021년 23주차 1월4주차 1월22일: 66.34%; 2021년 24주차 1월5주차 1월29일: 67.56%; 2021년 25주차 2월1주차 2월5일: 71.88%; 2021년 26주차 2월2주차 2월12일: 72.5%; 2021년 27주차 2월3주차 2월19일: 73.12%; 2021년 28주차 2월4주차 2월26일: 73.74%; 2021년 29주차 3월1주차 3월5일: 75.35%; 2021년 30주차 3월2주차 3월12일: 75.97%; 2021년 31주차 3월3주차 3월19일: 76.59%; 2021년 32주차 3월4주차 3월26일: 77.21%; 2021년 33주차 4월1주차 4월2일: 78.82%; 2021년 34주차 4월2주차 4월9일: 79.44%; 2021년 35주차 4월3주차 4월16일: 80.91%; 2021년 36주차 4월4주차 4월23일: 83.49%; 2021년 37주차 4월5주차 4월30일: 86.3%; 2021년 38주차 5월1주차 5월7일: 86.92%; 2021년 39주차 5월2주차 5월14일: 89.29%; 2021년 40주차 5월3주차 5월21일: 92.16%; 2021년 41주차 5월4주차 5월28일: 93.28%; 2021년 42주차 6월1주차 6월4일: 99.08%; 2021년 43주차 6월2주차 6월10일: 100%
프로젝트 착수 | 5% |  |  | 2021-08-24 | 2021-11-20 | 홍성우 | 0% | 85% | 91% | 91% | 94% | 94% | 94% | 94% | 94% | 94% | 94% | 97% | 97% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 4.25% | 4.55% | 4.55% | 4.7% | 4.7% | 4.7% | 4.7% | 4.7% | 4.7% | 4.7% | 4.85% | 4.85% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5%
착수계 제출 |  | 100% |  | 2021-08-24 | 2021-11-20 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
착수계 및 공문제출 | 5% |  | 5% | 2021-08-24 | 2021-08-28 |  | 2020년 2주차 8월5주차 8월28일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 5%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 착수계
사업수행계획서 작성 및 제출 | 80% |  | 80% | 2021-08-24 | 2021-08-28 |  | 2020년 2주차 8월5주차 8월28일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 80%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 사업수행계획서
상주인력 투입 | 15% |  | 15% | 2021-08-31 | 2021-11-20 |  | 2020년 3주차 9월1주차 9월4일: 40%; 2020년 5주차 9월3주차 9월18일: 20%; 2020년 12주차 11월1주차 11월6일: 20%; 2020년 14주차 11월3주차 11월 20일: 20%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 6%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 3%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 3%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 3%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 투입인력계획
프로젝트 표준 정의 | 10% |  |  | 2021-08-31 | 2021-10-02 | 홍성우, 박운하 | 0% | 0% | 19.8% | 59.6% | 95.2% | 98.8% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 1.98% | 5.96% | 9.52% | 9.88% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
표준화 관리 |  | 30% |  | 2021-08-31 | 2021-10-02 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
프로젝트 문서표준 및 절차 정의 | 9% |  | 30% | 2021-08-31 | 2021-09-11 |  | 2020년 3주차 9월1주차 9월4일: 70%; 2020년 4주차 9월2주차 9월11일: 30%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 6.3%; 2020년 4주차 9월2주차 9월11일: 2.7%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 프로젝트 문서표준 및 절차서
공정 및 산출물 테일러링 | 9% |  | 30% | 2021-08-31 | 2021-09-11 |  | 2020년 3주차 9월1주차 9월4일: 50%; 2020년 4주차 9월2주차 9월11일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 4.5%; 2020년 4주차 9월2주차 9월11일: 4.5%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 산출물테일러링결과서
산출물 표준 샘플 양식 작성 | 12% |  | 40% | 2021-09-07 | 2021-10-02 |  | 2020년 4주차 9월2주차 9월11일: 30%; 2020년 5주차 9월3주차 9월18일: 30%; 2020년 6주차 9월4주차 9월25일: 30%; 2020년 7주차 10월1주차 10월2일: 10%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 3.6%; 2020년 5주차 9월3주차 9월18일: 3.6%; 2020년 6주차 9월4주차 9월25일: 3.6%; 2020년 7주차 10월1주차 10월2일: 1.2%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 문서양식 샘플
사업관리 계획 수립 |  | 30% |  | 2021-08-31 | 2021-09-18 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
위험관리계획 수립 | 6% |  | 20% | 2021-08-31 | 2021-09-18 |  | 2020년 3주차 9월1주차 9월4일: 30%; 2020년 4주차 9월2주차 9월11일: 30%; 2020년 5주차 9월3주차 9월18일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 1.8%; 2020년 4주차 9월2주차 9월11일: 1.8%; 2020년 5주차 9월3주차 9월18일: 2.4%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 위험관리계획서
형상관리계획 수립 | 6% |  | 20% | 2021-08-31 | 2021-09-18 |  | 2020년 3주차 9월1주차 9월4일: 30%; 2020년 4주차 9월2주차 9월11일: 30%; 2020년 5주차 9월3주차 9월18일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 1.8%; 2020년 4주차 9월2주차 9월11일: 1.8%; 2020년 5주차 9월3주차 9월18일: 2.4%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 형상관리계획서
품질관리계획 수립 | 6% |  | 20% | 2021-08-31 | 2021-09-18 |  | 2020년 3주차 9월1주차 9월4일: 30%; 2020년 4주차 9월2주차 9월11일: 30%; 2020년 5주차 9월3주차 9월18일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 1.8%; 2020년 4주차 9월2주차 9월11일: 1.8%; 2020년 5주차 9월3주차 9월18일: 2.4%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 품질관리계획서
교육관리계획 수립 | 6% |  | 20% | 2021-08-31 | 2021-09-18 |  | 2020년 3주차 9월1주차 9월4일: 30%; 2020년 4주차 9월2주차 9월11일: 30%; 2020년 5주차 9월3주차 9월18일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 1.8%; 2020년 4주차 9월2주차 9월11일: 1.8%; 2020년 5주차 9월3주차 9월18일: 2.4%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 교육관리계획서
보안관리계획 수립 | 6% |  | 20% | 2021-08-31 | 2021-09-18 |  | 2020년 3주차 9월1주차 9월4일: 30%; 2020년 4주차 9월2주차 9월11일: 30%; 2020년 5주차 9월3주차 9월18일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 1.8%; 2020년 4주차 9월2주차 9월11일: 1.8%; 2020년 5주차 9월3주차 9월18일: 2.4%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 보안관리계획서
프로젝트 일정계획 수립 |  | 40% |  | 2021-09-07 | 2021-09-18 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
WBS 작성 | 28% |  | 70% | 2021-09-07 | 2021-09-18 |  | 2020년 4주차 9월2주차 9월11일: 50%; 2020년 5주차 9월3주차 9월18일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 14%; 2020년 5주차 9월3주차 9월18일: 14%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | WBS
WBS 고객 검토 및 확정 | 12% |  | 30% | 2021-09-07 | 2021-09-18 |  | 2020년 4주차 9월2주차 9월11일: 50%; 2020년 5주차 9월3주차 9월18일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 6%; 2020년 5주차 9월3주차 9월18일: 6%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | WBS
교육관리 | 10% |  |  | 2021-09-21 | 2021-01-01 | 홍성우 | 0% | 0% | 0% | 0% | 0% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 25% | 34% | 55% | 55% | 77.5% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 2.5% | 3.4% | 5.5% | 5.5% | 7.75% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
개발자 교육 |  | 100% |  | 2021-09-21 | 2021-01-01 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
프로젝트 문서 표준 및 절차, 형상/위험관리 | 10% |  | 10% | 2021-09-21 | 2021-09-25 |  | 2020년 6주차 9월4주차 9월25일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 10%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 교육결과서
개발산출물 작성 교육 | 15% |  | 15% | 2021-09-21 | 2021-09-25 |  | 2020년 6주차 9월4주차 9월25일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 15%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 교육결과서
개발표준(시큐어코딩) 교육 | 15% |  | 15% | 2021-12-21 | 2021-01-01 |  | 2020년 19주차 12월4주차 12월25일: 50%; 2021년 20주차 1월1주차 1월1일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 7.5%; 2021년 20주차 1월1주차 1월1일: 7.5%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 교육결과서
웹접근성표준 교육 | 15% |  | 15% | 2021-12-21 | 2021-01-01 |  | 2020년 19주차 12월4주차 12월25일: 50%; 2021년 20주차 1월1주차 1월1일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 7.5%; 2021년 20주차 1월1주차 1월1일: 7.5%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 교육결과서
UI 표준 교육 | 15% |  | 15% | 2021-12-21 | 2021-01-01 |  | 2020년 19주차 12월4주차 12월25일: 50%; 2021년 20주차 1월1주차 1월1일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 7.5%; 2021년 20주차 1월1주차 1월1일: 7.5%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 교육결과서
웹에디터(사이냅) 교육 | 15% |  | 15% | 2021-11-30 | 2021-12-11 |  | 2020년 16주차 12월1주차 12월4일: 30%; 2020년 17주차 12월2주차 12월11일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 4.5%; 2020년 17주차 12월2주차 12월11일: 10.5%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 교육결과서
검색엔진 교육 | 15% |  | 15% | 2021-11-30 | 2021-12-11 |  | 2020년 16주차 12월1주차 12월4일: 30%; 2020년 17주차 12월2주차 12월11일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 4.5%; 2020년 17주차 12월2주차 12월11일: 10.5%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 교육결과서
범위관리 | 10% |  |  | 2021-08-31 | 2021-11-13 | 홍성우, 조한빈 | 0% | 0% | 5% | 5% | 5% | 5% | 5% | 5% | 23% | 65% | 75% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 2.3% | 6.5% | 7.5% | 9.5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
요구사항 관리 |  | 100% |  | 2021-08-31 | 2021-11-13 | 조한빈 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
과업대비표 작성 및 고객검토 | 10% |  | 10% | 2021-08-31 | 2021-11-13 |  | 2020년 3주차 9월1주차 9월4일: 50%; 2020년 13주차 11월2주차 11월13일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 5%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 5%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 과업대비표
요구사항정의서 작성 및 고객검토 | 60% |  | 60% | 2021-10-12 | 2021-10-23 |  | 2020년 9주차 10월3주차 10월 16일: 30%; 2020년 10주차 10월4주차 10월 23일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 18%; 2020년 10주차 10월4주차 10월 23일: 42%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 요구사항정의서
요구사항 추적관리 | 10% |  | 10% | 2021-10-26 | 2021-10-30 |  | 2020년 11주차 10월5주차 10월30일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 10%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 요구사항추적매트릭스
검사기준서 작성 및 고객검토 | 20% |  | 20% | 2021-11-02 | 2021-11-06 |  | 2020년 12주차 11월1주차 11월6일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 20%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 검사기준서
품질관리 | 20% |  |  | 2021-12-07 | 2021-05-21 | 홍성우 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.15% | 10.5% | 20.25% | 32.5% | 40% | 45.25% | 52% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 55% | 59.2% | 69% | 75% | 75% | 83.75% | 95% | 97.5% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.63% | 2.1% | 4.05% | 6.5% | 8% | 9.05% | 10.4% | 11% | 11% | 11% | 11% | 11% | 11% | 11% | 11% | 11% | 11% | 11% | 11.84% | 13.8% | 15% | 15% | 16.75% | 19% | 19.5% | 20% | 20%
분석단계 |  | 15% |  | 2021-12-07 | 2021-12-25 | 홍성우 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
품질점검 | 10.5% |  | 70% | 2021-12-07 | 2021-12-18 |  | 2020년 17주차 12월2주차 12월11일: 30%; 2020년 18주차 12월3주차 12월18일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 3.15%; 2020년 18주차 12월3주차 12월18일: 7.35%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 품질점검결과서
조치결과 확인 | 4.5% |  | 30% | 2021-12-21 | 2021-12-25 |  | 2020년 19주차 12월4주차 12월25일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 4.5%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 품질점검결과서
중간감리 |  | 15% |  | 2021-01-11 | 2021-01-29 | 홍성우 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
중간감리 수검 | 5.25% |  | 35% | 2021-01-11 | 2021-01-15 |  | 2021년 22주차 1월3주차 1월15일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 5.25%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 감리보고서
중간감리 조치계획 수립 | 1.5% |  | 10% | 2021-01-04 | 2021-01-08 |  | 2021년 23주차 1월4주차 1월22일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 1.5%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 감리조치계획서
중간감리 조치 | 5.25% |  | 35% | 2021-01-04 | 2021-01-08 |  | 2021년 23주차 1월4주차 1월22일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 5.25%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 감리조치결과서
중간감리 조치결과서 작성 및 제출 | 3% |  | 20% | 2021-01-11 | 2021-01-15 |  | 2021년 24주차 1월5주차 1월29일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 3%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 감리조치결과서
설계단계 |  | 25% |  | 2021-12-21 | 2021-01-01 | 홍성우 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
품질점검 | 17.5% |  | 70% | 2021-12-21 | 2021-01-01 |  | 2020년 19주차 12월4주차 12월25일: 30%; 2021년 20주차 1월1주차 1월1일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 5.25%; 2021년 20주차 1월1주차 1월1일: 12.25%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 품질점검결과서
조치결과 확인 | 7.5% |  | 30% | 2021-01-04 | 2021-01-08 |  | 2021년 21주차 1월2주차 1월8일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 7.5%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 품질점검결과서
최종감리 |  | 25% |  | 2021-05-10 | 2021-05-25 | 홍성우 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
최종감리 수검 | 8.75% |  | 35% | 2021-05-10 | 2021-05-14 |  | 2021년 39주차 5월2주차 5월14일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 8.75%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 감리보고서
최종감리 조치계획 수립 | 2.5% |  | 10% | 2021-05-17 | 2021-05-19 |  | 2021년 40주차 5월3주차 5월21일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 2.5%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 감리조치계획서
최종감리 조치 | 8.75% |  | 35% | 2021-05-17 | 2021-05-21 |  | 2021년 40주차 5월3주차 5월21일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 8.75%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 감리조치결과서
최종감리 조치결과서 작성 및 제출 | 5% |  | 20% | 2021-05-20 | 2021-05-25 |  | 2021년 41주차 5월4주차 5월28일: 50%; 2021년 42주차 6월1주차 6월4일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 2.5%; 2021년 42주차 6월1주차 6월4일: 2.5%; 2021년 43주차 6월2주차 6월10일: 0% | 감리조치결과서
개발/시험단계 |  | 20% |  | 2021-04-12 | 2021-04-30 | 홍성우 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
품질점검 | 14% |  | 70% | 2021-04-12 | 2021-04-23 |  | 2021년 35주차 4월3주차 4월16일: 30%; 2021년 36주차 4월4주차 4월23일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 4.2%; 2021년 36주차 4월4주차 4월23일: 9.8%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 품질점검결과서
조치결과 확인 | 6% |  | 30% | 2021-04-26 | 2021-04-30 |  | 2021년 37주차 4월5주차 4월30일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 6%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 품질점검결과서
사업관리(보고, 일정, 위험, 형상, 자원 포함) | 45% |  |  | 2021-08-17 | 2021-06-10 | 홍성우, 조한빈 | 1.38% | 2.76% | 4.14% | 5.52% | 6.9% | 14.28% | 17.86% | 19.24% | 20.62% | 22% | 25.58% | 26.96% | 28.34% | 29.72% | 31.1% | 34.68% | 36.06% | 37.44% | 38.82% | 42.4% | 43.78% | 45.16% | 46.54% | 47.92% | 57.5% | 58.88% | 60.26% | 61.64% | 65.22% | 66.6% | 67.98% | 69.36% | 72.94% | 74.32% | 75.7% | 77.08% | 80.66% | 82.04% | 83.42% | 84.8% | 86.18% | 97.96% | 100% | 0.621% | 1.242% | 1.863% | 2.484% | 3.105% | 6.426% | 8.037% | 8.658% | 9.279% | 9.9% | 11.51% | 12.13% | 12.75% | 13.37% | 14% | 15.61% | 16.23% | 16.85% | 17.47% | 19.08% | 19.7% | 20.32% | 20.94% | 21.56% | 25.88% | 26.5% | 27.12% | 27.74% | 29.35% | 29.97% | 30.59% | 31.21% | 32.82% | 33.44% | 34.06% | 34.69% | 36.3% | 36.92% | 37.54% | 38.16% | 38.78% | 44.08% | 45%
주간보고/일정/위험/형상/자원 관리 |  | 60% |  | 2021-08-17 | 2021-06-10 | 홍성우, 조한빈 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
1주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-08-17 | 2021-08-21 |  | 2020년 1주차 8월4주차 8월21일: 100%; 2020년 1주차 8월4주차 8월21일: 1.38%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 주간업무보고서, WBS진척율, 위험/이슈관리대장, 형상항목정의서, 변경요청서 등
2주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-08-24 | 2021-08-28 |  | 2020년 2주차 8월5주차 8월28일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 1.38%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
3주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-08-31 | 2021-09-04 |  | 2020년 3주차 9월1주차 9월4일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 1.38%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
4주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-09-07 | 2021-09-11 |  | 2020년 4주차 9월2주차 9월11일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 1.38%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
5주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-09-14 | 2021-09-18 |  | 2020년 5주차 9월3주차 9월18일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 1.38%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
6주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-09-21 | 2021-09-25 |  | 2020년 6주차 9월4주차 9월25일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 1.38%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
7주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-09-28 | 2021-10-02 |  | 2020년 7주차 10월1주차 10월2일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 1.38%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
8주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-10-05 | 2021-10-09 |  | 2020년 8주차 10월2주차 10월9일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 1.38%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
9주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-10-12 | 2021-10-16 |  | 2020년 9주차 10월3주차 10월 16일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 1.38%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
10주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-10-19 | 2021-10-23 |  | 2020년 10주차 10월4주차 10월 23일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 1.38%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
11주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-10-26 | 2021-10-30 |  | 2020년 11주차 10월5주차 10월30일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 1.38%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
12주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-11-02 | 2021-11-06 |  | 2020년 12주차 11월1주차 11월6일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 1.38%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
13주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-11-09 | 2021-11-13 |  | 2020년 13주차 11월2주차 11월13일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 1.38%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
14주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-11-16 | 2021-11-20 |  | 2020년 14주차 11월3주차 11월 20일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 1.38%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
15주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-11-23 | 2021-11-27 |  | 2020년 15주차 11월4주차 11월27일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 1.38%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
16주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-11-30 | 2021-12-04 |  | 2020년 16주차 12월1주차 12월4일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 1.38%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
17주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-12-07 | 2021-12-11 |  | 2020년 17주차 12월2주차 12월11일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 1.38%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
18주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-12-14 | 2021-12-18 |  | 2020년 18주차 12월3주차 12월18일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 1.38%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
19주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-12-21 | 2021-12-25 |  | 2020년 19주차 12월4주차 12월25일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 1.38%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
20주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2021-12-28 | 2022-01-01 |  | 2021년 20주차 1월1주차 1월1일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 1.38%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
21주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-01-04 | 2022-01-08 |  | 2021년 21주차 1월2주차 1월8일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 1.38%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
22주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-01-11 | 2022-01-15 |  | 2021년 22주차 1월3주차 1월15일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 1.38%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
23주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-01-18 | 2022-01-22 |  | 2021년 23주차 1월4주차 1월22일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 1.38%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
24주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-01-25 | 2022-01-29 |  | 2021년 24주차 1월5주차 1월29일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 1.38%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
25주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-02-01 | 2022-02-05 |  | 2021년 25주차 2월1주차 2월5일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 1.38%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
26주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-02-08 | 2022-02-12 |  | 2021년 26주차 2월2주차 2월12일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 1.38%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
27주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-02-15 | 2022-02-19 |  | 2021년 27주차 2월3주차 2월19일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 1.38%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
28주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-02-22 | 2022-02-26 |  | 2021년 28주차 2월4주차 2월26일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 1.38%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
29주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-03-01 | 2022-03-05 |  | 2021년 29주차 3월1주차 3월5일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 1.38%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
30주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-03-08 | 2022-03-12 |  | 2021년 30주차 3월2주차 3월12일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 1.38%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
31주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-03-15 | 2022-03-19 |  | 2021년 31주차 3월3주차 3월19일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 1.38%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
32주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-03-22 | 2022-03-26 |  | 2021년 32주차 3월4주차 3월26일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 1.38%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
33주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-03-29 | 2022-04-02 |  | 2021년 33주차 4월1주차 4월2일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 1.38%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
34주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-04-05 | 2022-04-09 |  | 2021년 34주차 4월2주차 4월9일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 1.38%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
35주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-04-12 | 2022-04-16 |  | 2021년 35주차 4월3주차 4월16일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 1.38%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
36주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-04-19 | 2022-04-23 |  | 2021년 36주차 4월4주차 4월23일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 1.38%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
37주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-04-26 | 2022-04-30 |  | 2021년 37주차 4월5주차 4월30일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 1.38%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
38주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-05-03 | 2022-05-07 |  | 2021년 38주차 5월1주차 5월7일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 1.38%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
39주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-05-10 | 2022-05-14 |  | 2021년 39주차 5월2주차 5월14일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 1.38%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
40주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-05-17 | 2022-05-21 |  | 2021년 40주차 5월3주차 5월21일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 1.38%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
41주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-05-24 | 2022-05-28 |  | 2021년 41주차 5월4주차 5월28일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 1.38%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
42주차 주간보고/일정/위험/형상/자원 관리 | 1.38% |  | 2.3% | 2022-05-31 | 2022-06-04 |  | 2021년 42주차 6월1주차 6월4일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 1.38%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
43주차 주간보고/일정/위험/형상/자원 관리 | 2.04% |  | 3.4% | 2022-06-07 | 2021-06-10 |  | 2021년 43주차 6월2주차 6월10일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 2.04% | 상동
월간업무보고 |  | 20% |  | 2021-09-28 | 2021-06-04 | 홍성우 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
09월 월간업무보고 | 2.2% |  | 11% | 2021-09-28 | 2021-10-02 |  | 2020년 7주차 10월1주차 10월2일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 2.2%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 월간업무보고서, 투입인력결과
10월 월간업무보고 | 2.2% |  | 11% | 2021-10-26 | 2021-10-30 |  | 2020년 11주차 10월5주차 10월30일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 2.2%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
11월 월간업무보고 | 2.2% |  | 11% | 2021-11-30 | 2021-12-04 |  | 2020년 16주차 12월1주차 12월4일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 2.2%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
12월 월간업무보고 | 2.2% |  | 11% | 2021-12-28 | 2021-01-01 |  | 2021년 20주차 1월1주차 1월1일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 2.2%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
1월 월간업무보고 | 2.2% |  | 11% | 2021-02-01 | 2021-02-05 |  | 2021년 25주차 2월1주차 2월5일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 2.2%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
2월 월간업무보고 | 2.2% |  | 11% | 2021-03-01 | 2021-03-05 |  | 2021년 29주차 3월1주차 3월5일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 2.2%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
3월 월간업무보고 | 2.2% |  | 11% | 2021-03-29 | 2021-04-02 |  | 2021년 33주차 4월1주차 4월2일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 2.2%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
4월 월간업무보고 | 2.2% |  | 11% | 2021-04-26 | 2021-04-30 |  | 2021년 37주차 4월5주차 4월30일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 2.2%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
5월 월간업무보고 | 2.4% |  | 12% | 2021-05-31 | 2021-06-04 |  | 2021년 42주차 6월1주차 6월4일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 2.4%; 2021년 43주차 6월2주차 6월10일: 0% | 상동
착수/중간/종료보고 |  | 20% |  | 2021-09-21 | 2021-06-04 | 홍성우 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
착수보고 | 6% |  | 30% | 2021-09-21 | 2021-09-25 |  | 2020년 6주차 9월4주차 9월25일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 6%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 착수보고서
중간보고 | 6% |  | 30% | 2021-02-01 | 2021-02-05 |  | 2021년 25주차 2월1주차 2월5일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 6%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 중간보고서
종료보고 | 8% |  | 40% | 2021-05-31 | 2021-06-04 |  | 2021년 42주차 6월1주차 6월4일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 8%; 2021년 43주차 6월2주차 6월10일: 0% | 최종보고서

## 공통(계획)
공정명 | 중요도 |  |  | 시작예정일 | 종료예정일 | 업무담당 | 산출물 | 2020년 | [18 empty] | 2021년 | [23 empty] | 2020년 | [18 empty] | 2021년
[8 empty] | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차 | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차
[8 empty] | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차 | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차
| Stage | Step | Task |  |  |  |  | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일 | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일
평가 및 교류협력 | [7 empty] | 2020년 1주차 8월4주차 8월21일: #REF!; 2020년 2주차 8월5주차 8월28일: #REF!; 2020년 3주차 9월1주차 9월4일: #REF!; 2020년 4주차 9월2주차 9월11일: #REF!; 2020년 5주차 9월3주차 9월18일: #REF!; 2020년 6주차 9월4주차 9월25일: #REF!; 2020년 7주차 10월1주차 10월2일: #REF!; 2020년 8주차 10월2주차 10월9일: #REF!; 2020년 9주차 10월3주차 10월 16일: #REF!; 2020년 10주차 10월4주차 10월 23일: #REF!; 2020년 11주차 10월5주차 10월30일: #REF!; 2020년 12주차 11월1주차 11월6일: #REF!; 2020년 13주차 11월2주차 11월13일: #REF!; 2020년 14주차 11월3주차 11월 20일: #REF!; 2020년 15주차 11월4주차 11월27일: #REF!; 2020년 16주차 12월1주차 12월4일: #REF!; 2020년 17주차 12월2주차 12월11일: #REF!; 2020년 18주차 12월3주차 12월18일: #REF!; 2020년 19주차 12월4주차 12월25일: #REF!; 2021년 20주차 1월1주차 1월1일: #REF!; 2021년 21주차 1월2주차 1월8일: #REF!; 2021년 22주차 1월3주차 1월15일: #REF!; 2021년 23주차 1월4주차 1월22일: #REF!; 2021년 24주차 1월5주차 1월29일: #REF!; 2021년 25주차 2월1주차 2월5일: #REF!; 2021년 26주차 2월2주차 2월12일: #REF!; 2021년 27주차 2월3주차 2월19일: #REF!; 2021년 28주차 2월4주차 2월26일: #REF!; 2021년 29주차 3월1주차 3월5일: #REF!; 2021년 30주차 3월2주차 3월12일: #REF!; 2021년 31주차 3월3주차 3월19일: #REF!; 2021년 32주차 3월4주차 3월26일: #REF!; 2021년 33주차 4월1주차 4월2일: #REF!; 2021년 34주차 4월2주차 4월9일: #REF!; 2021년 35주차 4월3주차 4월16일: #REF!; 2021년 36주차 4월4주차 4월23일: #REF!; 2021년 37주차 4월5주차 4월30일: #REF!; 2021년 38주차 5월1주차 5월7일: #REF!; 2021년 39주차 5월2주차 5월14일: #REF!; 2021년 40주차 5월3주차 5월21일: #REF!; 2021년 41주차 5월4주차 5월28일: #REF!; 2021년 42주차 6월1주차 6월4일: #REF!; 2021년 43주차 6월2주차 6월10일: #REF!
요구정의 | 10% |  |  | 2021-09-13 | 2021-10-01 |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 2.5% | 5% | 7.5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10%
요구사항정의 |  | 100% |  | 2021-09-13 | 2021-10-01 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
요구사항 정의 | 80% |  | 80% | 2021-09-13 | 2021-09-28 | 홍성우, 김수혜 | 요구사항정의서 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 20%; 2020년 7주차 10월1주차 10월2일: 20%; 2020년 8주차 10월2주차 10월9일: 20%; 2020년 9주차 10월3주차 10월 16일: 20%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
요구사항 확정 | 20% |  | 20% | 2021-09-29 | 2021-10-01 | 홍성우, 김수혜 | 요구사항정의서 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 5%; 2020년 7주차 10월1주차 10월2일: 5%; 2020년 8주차 10월2주차 10월9일: 5%; 2020년 9주차 10월3주차 10월 16일: 5%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0% | 1.6333
분석 | 12% |  |  | 2021-10-04 | 2021-10-15 |  |  | 0% | 0% | 0% | 0% | 0% | 25% | 50% | 75% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 3% | 6% | 9% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12% | 12%
테스트 계획 |  | 100% |  | 2021-10-04 | 2021-10-15 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
총괄테스트 계획 수립 | 100% |  | 100% | 2021-10-04 | 2021-10-15 | 홍성우 | 총괄테스트계획서 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
설계 | 30% |  |  | 2021-10-18 | 2021-10-20 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 30% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 3.6% | 9% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18% | 18%
시스템 구조 설계 |  | 60% |  | 2021-10-18 | 2021-10-20 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
아키텍처 설계 | 60% |  | 100% | 2021-10-18 | 2021-10-22 | 홍성우, 김수혜 | 아키텍처정의서 | 2020년 13주차 11월2주차 11월13일: 20%; 2020년 14주차 11월3주차 11월 20일: 30%; 2020년 15주차 11월4주차 11월27일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 12%; 2020년 14주차 11월3주차 11월 20일: 18%; 2020년 15주차 11월4주차 11월27일: 30%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
시험 설계 |  | 40% |  | 2021-11-01 | 2021-11-05 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
검사기준 정의(비기능공통) | 40% |  | 100% | 2021-11-01 | 2021-11-05 | 홍성우, 김수혜 | 검사기준서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시험 | 30% |  |  | 2021-11-29 | 2021-12-10 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 15% | 30% | 50% | 50% | 50% | 50% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 4.5% | 9% | 15% | 15% | 15% | 15%
시스템테스트 |  | 100% |  | 2021-11-29 | 2021-12-10 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시큐어코딩/웹취약점 조치 | 50% |  | 50% | 2021-11-29 | 2021-12-10 | 홍성우 | 시큐어코딩, 웹취약점 점검결과서
성능테스트 수행 | 50% |  | 50% | 2021-11-29 | 2021-12-10 | 홍성우 | 성능테스트 계획서/결과서 | 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 30%; 2021년 40주차 5월3주차 5월21일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 15%; 2021년 39주차 5월2주차 5월14일: 15%; 2021년 40주차 5월3주차 5월21일: 20%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
이행 | 18% |  |  | 2021-11-01 | 2021-12-31 |  |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 40% | 70% | 70% | 70% | 70% | 70% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.16% | 7.2% | 12.6% | 12.6% | 12.6% | 12.6% | 12.6%
HW/SW 납품 |  | 100% |  | 2021-11-01 | 2021-12-10 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
IPSEC-VPN 설치 | 40% |  | 40% | 2021-11-01 | 2021-12-10 | 수행업체 | 라이선스증서, 설치확인서, 기술지원확약서, 제품보증서 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 12%; 2021년 38주차 5월1주차 5월7일: 28%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
다차원분석솔루션 설치 | 30% |  | 30% | 2021-11-02 | 2021-12-10 | 수행업체 | 라이선스증서, 설치확인서, 기술지원확약서, 제품보증서 | 2021년 39주차 5월2주차 5월14일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 30%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
통계 솔루션 설치 | 30% |  | 30% | 2021-11-03 | 2021-12-10 | 수행업체 | 라이선스증서, 설치확인서, 기술지원확약서, 제품보증서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
하자보수계획 |  | 100% |  | 2021-12-20 | 2021-12-24 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
하자보수계획 | 100% |  | 100% | 2021-12-20 | 2021-12-24 | 홍성우 | 하자보수 및 유지관리계획서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일

## 화상평가(계획)
공정명 | 중요도 |  |  | 시작예정일 | 종료예정일 | 업무담당 | 산출물 | 2020년 | [18 empty] | 2021년 | [23 empty] | 2020년 | [18 empty] | 2021년
[8 empty] | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차 | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차
[8 empty] | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차 | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차
| Stage | Step | Task |  |  |  |  | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일 | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일
평가 및 교류협력 | [7 empty] | 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 1%; 2020년 7주차 10월1주차 10월2일: 2%; 2020년 8주차 10월2주차 10월9일: 3%; 2020년 9주차 10월3주차 10월 16일: 4%; 2020년 10주차 10월4주차 10월 23일: 4%; 2020년 11주차 10월5주차 10월30일: 4%; 2020년 12주차 11월1주차 11월6일: 4%; 2020년 13주차 11월2주차 11월13일: 4%; 2020년 14주차 11월3주차 11월 20일: 4.396%; 2020년 15주차 11월4주차 11월27일: 5.188%; 2020년 16주차 12월1주차 12월4일: 5.98%; 2020년 17주차 12월2주차 12월11일: 6.772%; 2020년 18주차 12월3주차 12월18일: 7.96%; 2020년 19주차 12월4주차 12월25일: 8.752%; 2021년 20주차 1월1주차 1월1일: 10.6%; 2021년 21주차 1월2주차 1월8일: 10.68%; 2021년 22주차 1월3주차 1월15일: 10.75%; 2021년 23주차 1월4주차 1월22일: 10.83%; 2021년 24주차 1월5주차 1월29일: 10.9%; 2021년 25주차 2월1주차 2월5일: 11.05%; 2021년 26주차 2월2주차 2월12일: 11.2%; 2021년 27주차 2월3주차 2월19일: 11.35%; 2021년 28주차 2월4주차 2월26일: 11.5%; 2021년 29주차 3월1주차 3월5일: 11.65%; 2021년 30주차 3월2주차 3월12일: 11.8%; 2021년 31주차 3월3주차 3월19일: 11.95%; 2021년 32주차 3월4주차 3월26일: 12.1%; 2021년 33주차 4월1주차 4월2일: 12.1%; 2021년 34주차 4월2주차 4월9일: 12.1%; 2021년 35주차 4월3주차 4월16일: 14.86%; 2021년 36주차 4월4주차 4월23일: 21.3%; 2021년 37주차 4월5주차 4월30일: 25.32%; 2021년 38주차 5월1주차 5월7일: 30.31%; 2021년 39주차 5월2주차 5월14일: 36.78%; 2021년 40주차 5월3주차 5월21일: 37.89%; 2021년 41주차 5월4주차 5월28일: 38.33%; 2021년 42주차 6월1주차 6월4일: 39.07%; 2021년 43주차 6월2주차 6월10일: 39.8%
요구정의 | 8% |  |  | 2021-09-13 | 2021-10-01 | 화상평가 |  | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 0% | 0% | 0% | 0% | 0% | 0.8% | 1.6% | 2.4% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2%
요구사항정의 |  | 100% |  | 2021-09-13 | 2021-10-01 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
요구사항 정의 | 32% |  | 80% | 2021-09-13 | 2021-09-28 | 홍성우, 최현규 | 요구사항정의서 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 8%; 2020년 7주차 10월1주차 10월2일: 8%; 2020년 8주차 10월2주차 10월9일: 8%; 2020년 9주차 10월3주차 10월 16일: 8%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
요구사항 확정 | 8% |  | 20% | 2021-09-29 | 2021-10-01 | 홍성우, 최현규 | 요구사항정의서 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 2%; 2020년 7주차 10월1주차 10월2일: 2%; 2020년 8주차 10월2주차 10월9일: 2%; 2020년 9주차 10월3주차 10월 16일: 2%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
분석 | 10% |  |  | 2021-10-04 | 2021-10-15 | 화상평가 |  | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 0% | 0% | 0% | 0% | 0% | 1% | 2% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4%
업무 분석 |  | 40% |  | 2021-10-04 | 2021-10-08 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
업무 절차 분석 | 40% |  | 100% | 2021-10-04 | 2021-10-08 | 최현규 | 업무흐름도 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 10%; 2020년 7주차 10월1주차 10월2일: 10%; 2020년 8주차 10월2주차 10월9일: 10%; 2020년 9주차 10월3주차 10월 16일: 10%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
데이터 분석 |  | 50% |  | 2021-10-11 | 2021-10-15 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
논리데이터 모델링 | 50% |  | 100% | 2021-10-11 | 2021-10-15 | 홍성우 | 논리-ERD | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
UI 분석 |  | 10% |  | 2021-10-11 | 2021-10-15 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
메뉴구성도 | 10% |  | 100% | 2021-10-11 | 2021-10-15 | 최현규 | 메뉴구성도 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
설계 | 22% |  |  | 2021-10-18 | 2021-11-05 | 화상평가 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.8% | 5.4% | 9% | 12.6% | 18% | 21.6% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 30% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.396% | 1.188% | 1.98% | 2.772% | 3.96% | 4.752% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6% | 6.6%
데이터 설계 |  | 30% |  | 2021-10-18 | 2021-10-20 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
물리 데이터 모델링 | 18% |  | 60% | 2021-10-18 | 2021-10-20 | 홍성우 | 물리-ERD | 2020년 14주차 11월3주차 11월 20일: 10%; 2020년 15주차 11월4주차 11월27일: 20%; 2020년 16주차 12월1주차 12월4일: 20%; 2020년 17주차 12월2주차 12월11일: 20%; 2020년 18주차 12월3주차 12월18일: 30%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 1.8%; 2020년 15주차 11월4주차 11월27일: 3.6%; 2020년 16주차 12월1주차 12월4일: 3.6%; 2020년 17주차 12월2주차 12월11일: 3.6%; 2020년 18주차 12월3주차 12월18일: 5.4%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
테이블/코드설계 | 0% |  | 40% | 2021-10-21 | 2021-10-22 | 홍성우 | 테이블정의서, 코드정의서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
프로그램 설계 |  | 40% |  | 2021-10-18 | 2021-10-20 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
프로그램 설계 | 12% |  | 30% | 2021-10-18 | 2021-10-20 | 최현규 | 프로그램목록/설계서 | 2020년 19주차 12월4주차 12월25일: 30%; 2021년 20주차 1월1주차 1월1일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 3.6%; 2021년 20주차 1월1주차 1월1일: 8.4%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
화면설계 | 20% |  | 50% | 2021-10-21 | 2021-10-22 | 최현규 | 화면목록/설계서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
인터페이스 설계 | 8% |  | 20% | 2021-10-21 | 2021-10-22 | 최현규 | 인터페이스목록/정의서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시험 설계 |  | 30% |  | 2021-10-25 | 2021-10-29 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
단위테스트 설계 | 9% |  | 30% | 2021-10-25 | 2021-10-29 | 최현규 | 단위테스트케이스(계획) | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
통합 테스트 설계 | 15% |  | 50% | 2021-10-25 | 2021-10-29 | 최현규 | 통합테스트시나리오(계획) | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
검사기준 정의 | 6% |  | 20% | 2021-11-01 | 2021-11-05 | 최현규 | 검사기준서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
구현 | 30% |  |  | 2021-10-25 | 2021-12-03 | 화상평가 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25% | 0.5% | 0.75% | 1% | 1.5% | 2% | 2.5% | 3% | 3.5% | 4% | 4.5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.075% | 0.15% | 0.225% | 0.3% | 0.45% | 0.6% | 0.75% | 0.9% | 1.05% | 1.2% | 1.35% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5%
응용프로그램 구현 |  | 100% |  | 2021-10-25 | 2021-11-26 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
개발환경 구성 | 5% |  | 5% | 2021-10-25 | 2021-10-25 | 최현규 | 개발환경가이드 | [20 empty] | 5% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | [11 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25% | 0.25% | 0.25% | 0.25% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
개발(개발 상세일정을 별도 관리) | 75% |  | 75% | 2021-10-26 | 2021-11-26 | 최현규 | 소스 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
단위시험 수행 | 20% |  | 20% | 2021-11-01 | 2021-12-03 | 최현규 | 단위테스트케이스(결과) | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시험 | 23% |  |  | 2021-12-06 | 2021-12-24 | 화상평가 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 40% | 52% | 67% | 86% | 90% | 90% | 90% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.76% | 9.2% | 11.96% | 15.41% | 19.78% | 20.7% | 20.7% | 20.7% | 20.7%
통합테스트 |  | 40% |  | 2021-12-06 | 2021-12-10 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
통합테스트 수행 | 40% |  | 100% | 2021-12-06 | 2021-12-10 | 최현규 | 통합테스트시나리오(결과) | 2021년 35주차 4월3주차 4월16일: 30%; 2021년 36주차 4월4주차 4월23일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 12%; 2021년 36주차 4월4주차 4월23일: 28%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
시스템테스트 |  | 20% |  | 2021-12-13 | 2021-12-17 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시큐어코딩/웹취약점 조치 | 10% |  | 50% | 2021-12-13 | 2021-12-17 | 최현규 | 시큐어코딩, 웹취약점 점검 및 조치결과서
성능테스트 수행 | 10% |  | 50% | 2021-12-13 | 2021-12-17 | 최현규 | 성능테스트계획서/결과서 | 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 30%; 2021년 40주차 5월3주차 5월21일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 3%; 2021년 39주차 5월2주차 5월14일: 3%; 2021년 40주차 5월3주차 5월21일: 4%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
사용자테스트 |  | 40% |  | 2021-12-20 | 2021-12-24 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
사용자테스트 수행 | 40% |  | 100% | 2021-12-20 | 2021-12-24 | 최현규 | 사용자(승인)테스트결과서 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 12%; 2021년 38주차 5월1주차 5월7일: 12%; 2021년 39주차 5월2주차 5월14일: 16%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
이행 | 7% |  |  | 2021-12-13 | 2021-12-31 | 화상평가 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18% | 40% | 70% | 72.7% | 79% | 89.5% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.26% | 2.8% | 4.9% | 5.089% | 5.53% | 6.265% | 7%
이행 |  | 20% |  | 2021-12-13 | 2021-12-17 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
이행계획 수립 | 10% |  | 50% | 2021-12-13 | 2021-12-13 | 홍성우 | 이행계획서(시스템 오픈) | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 3%; 2021년 38주차 5월1주차 5월7일: 7%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
시스템 적용(시스템 오픈) | 10% |  | 50% | 2021-12-14 | 2021-12-17 | 최현규 | 이행결과서 | 2021년 39주차 5월2주차 5월14일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 10%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
매뉴얼 작성 |  | 50% |  | 2021-12-20 | 2021-12-24 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
사용자매뉴얼 작성 | 35% |  | 70% | 2021-12-20 | 2021-12-24 | 최현규 | 사용자매뉴얼 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 10.5%; 2021년 38주차 5월1주차 5월7일: 10.5%; 2021년 39주차 5월2주차 5월14일: 14%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
운영자매뉴얼 작성 | 15% |  | 30% | 2021-12-20 | 2021-12-24 | 최현규 | 운영자매뉴얼 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 4.5%; 2021년 38주차 5월1주차 5월7일: 4.5%; 2021년 39주차 5월2주차 5월14일: 6%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
인수인계 및 운영 |  | 30% |  | 2021-12-27 | 2021-12-31 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
사용자/운영자 교육훈련 실시 | 9% |  | 30% | 2021-12-27 | 2021-12-31 | 최현규 | 사용자교육결과서 | 2021년 40주차 5월3주차 5월21일: 30%; 2021년 41주차 5월4주차 5월28일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 2.7%; 2021년 41주차 5월4주차 5월28일: 6.3%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
운영지원 | 21% |  | 70% | 2021-12-27 | 2022-01-31 |  | 안정화 지원 | 2021년 42주차 6월1주차 6월4일: 50%; 2021년 43주차 6월2주차 6월10일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 10.5%; 2021년 43주차 6월2주차 6월10일: 10.5%

## 다차원분석(계획)
공정명 | 중요도 |  |  | 시작예정일 | 종료예정일 | 업무담당 | 산출물 | 2020년 | [18 empty] | 2021년 | [23 empty] | 2020년 | [18 empty] | 2021년
[8 empty] | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차 | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차
[8 empty] | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차 | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차
| Stage | Step | Task |  |  |  |  | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일 | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일
평가 및 교류협력 | [7 empty] | 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 1%; 2020년 7주차 10월1주차 10월2일: 2%; 2020년 8주차 10월2주차 10월9일: 3%; 2020년 9주차 10월3주차 10월 16일: 4%; 2020년 10주차 10월4주차 10월 23일: 4%; 2020년 11주차 10월5주차 10월30일: 4%; 2020년 12주차 11월1주차 11월6일: 4%; 2020년 13주차 11월2주차 11월13일: 4.462%; 2020년 14주차 11월3주차 11월 20일: 5.353%; 2020년 15주차 11월4주차 11월27일: 7.201%; 2020년 16주차 12월1주차 12월4일: 8.29%; 2020년 17주차 12월2주차 12월11일: 8.686%; 2020년 18주차 12월3주차 12월18일: 9.28%; 2020년 19주차 12월4주차 12월25일: 9.874%; 2021년 20주차 1월1주차 1월1일: 11.26%; 2021년 21주차 1월2주차 1월8일: 11.34%; 2021년 22주차 1월3주차 1월15일: 11.41%; 2021년 23주차 1월4주차 1월22일: 11.49%; 2021년 24주차 1월5주차 1월29일: 11.56%; 2021년 25주차 2월1주차 2월5일: 11.71%; 2021년 26주차 2월2주차 2월12일: 11.86%; 2021년 27주차 2월3주차 2월19일: 12.01%; 2021년 28주차 2월4주차 2월26일: 12.16%; 2021년 29주차 3월1주차 3월5일: 12.31%; 2021년 30주차 3월2주차 3월12일: 12.46%; 2021년 31주차 3월3주차 3월19일: 12.61%; 2021년 32주차 3월4주차 3월26일: 12.76%; 2021년 33주차 4월1주차 4월2일: 12.76%; 2021년 34주차 4월2주차 4월9일: 12.76%; 2021년 35주차 4월3주차 4월16일: 15.52%; 2021년 36주차 4월4주차 4월23일: 21.96%; 2021년 37주차 4월5주차 4월30일: 25.98%; 2021년 38주차 5월1주차 5월7일: 30.97%; 2021년 39주차 5월2주차 5월14일: 37.44%; 2021년 40주차 5월3주차 5월21일: 38.55%; 2021년 41주차 5월4주차 5월28일: 38.99%; 2021년 42주차 6월1주차 6월4일: 39.73%; 2021년 43주차 6월2주차 6월10일: 40.46%
요구정의 | 8% |  |  | 2021-09-13 | 2021-10-01 | 다차원분석 |  | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 0% | 0% | 0% | 0% | 0% | 0.8% | 1.6% | 2.4% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2%
요구사항정의 |  | 100% |  | 2021-09-13 | 2021-10-01 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
요구사항 정의 | 80% |  | 80% | 2021-09-13 | 2021-09-28 | 양승현 | 요구사항정의서 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 20%; 2020년 7주차 10월1주차 10월2일: 20%; 2020년 8주차 10월2주차 10월9일: 20%; 2020년 9주차 10월3주차 10월 16일: 20%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
요구사항 확정 | 20% |  | 20% | 2021-09-29 | 2021-10-01 | 양승현 | 요구사항정의서 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 5%; 2020년 7주차 10월1주차 10월2일: 5%; 2020년 8주차 10월2주차 10월9일: 5%; 2020년 9주차 10월3주차 10월 16일: 5%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
분석 | 10% |  |  | 2021-10-04 | 2021-10-15 | 다차원분석 |  | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 0% | 0% | 0% | 0% | 0% | 1% | 2% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4%
업무 분석 |  | 40% |  | 2021-10-04 | 2021-10-08 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
업무 절차 분석 | 40% |  | 100% | 2021-10-04 | 2021-10-08 | 양승현 | 업무흐름도 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 10%; 2020년 7주차 10월1주차 10월2일: 10%; 2020년 8주차 10월2주차 10월9일: 10%; 2020년 9주차 10월3주차 10월 16일: 10%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
데이터 분석 |  | 50% |  | 2021-10-11 | 2021-10-15 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
논리데이터 모델링 | 50% |  | 100% | 2021-10-11 | 2021-10-15 | 양승현 | 논리-ERD | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
UI 분석 |  | 10% |  | 2021-10-11 | 2021-10-15 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
메뉴구성도 | 10% |  | 100% | 2021-10-11 | 2021-10-15 | 김명훈 | 메뉴구성도 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
설계 | 22% |  |  | 2021-10-18 | 2021-01-01 | 다차원분석 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.1% | 6.15% | 14.55% | 19.5% | 21.3% | 24% | 26.7% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 33% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.462% | 1.353% | 3.201% | 4.29% | 4.686% | 5.28% | 5.874% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26% | 7.26%
시스템 구조 설계 |  | 15% |  | 2021-10-18 | 2021-10-20 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
아키텍처 설계 | 10.5% |  | 70% | 2021-10-18 | 2021-10-20 | 우현종, 양승현 | 아키텍처정의서 | 2020년 13주차 11월2주차 11월13일: 20%; 2020년 14주차 11월3주차 11월 20일: 30%; 2020년 15주차 11월4주차 11월27일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 2.1%; 2020년 14주차 11월3주차 11월 20일: 3.15%; 2020년 15주차 11월4주차 11월27일: 5.25%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
개발표준정의 | 4.5% |  | 30% | 2021-10-21 | 2021-10-22 | 양승현 | 개발표준정의정의서 | 2020년 15주차 11월4주차 11월27일: 30%; 2020년 16주차 12월1주차 12월4일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 1.35%; 2020년 16주차 12월1주차 12월4일: 3.15%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
데이터 설계 |  | 15% |  | 2021-10-25 | 2021-10-29 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
물리 데이터 모델링 | 9% |  | 60% | 2021-10-25 | 2021-10-29 | 양승현 | 물리-ERD | 2020년 14주차 11월3주차 11월 20일: 10%; 2020년 15주차 11월4주차 11월27일: 20%; 2020년 16주차 12월1주차 12월4일: 20%; 2020년 17주차 12월2주차 12월11일: 20%; 2020년 18주차 12월3주차 12월18일: 30%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0.9%; 2020년 15주차 11월4주차 11월27일: 1.8%; 2020년 16주차 12월1주차 12월4일: 1.8%; 2020년 17주차 12월2주차 12월11일: 1.8%; 2020년 18주차 12월3주차 12월18일: 2.7%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
테이블/코드설계 | 6% |  | 40% | 2021-10-25 | 2021-10-29 | 양승현 | 테이블정의서, 코드정의서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
프로그램 설계 |  | 30% |  | 2021-10-18 | 2021-10-29 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
프로그램 설계 | 9% |  | 30% | 2021-10-18 | 2021-10-22 |  | 프로그램목록/설계서 | 2020년 19주차 12월4주차 12월25일: 30%; 2021년 20주차 1월1주차 1월1일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 2.7%; 2021년 20주차 1월1주차 1월1일: 6.3%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
화면설계 | 15% |  | 50% | 2021-10-21 | 2021-10-22 | 송재익, 김명훈 | 화면목록/설계서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
인터페이스 설계 | 6% |  | 20% | 2021-10-25 | 2021-10-29 | 권영호 | 인터페이스목록/정의서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
UI 설계 |  | 20% |  | 2021-10-04 | 2021-10-15 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
화면 디자인 | 6% |  | 30% | 2021-10-04 | 2021-10-15 | 김소연 | 디자인시안 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
UI 표준정의 | 14% |  | 70% | 2021-10-18 | 2021-10-29 | 김소연 | 스타일가이드 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시험 설계 |  | 20% |  | 2021-10-25 | 2021-10-29 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
단위테스트 설계 | 6% |  | 30% | 2021-10-25 | 2021-10-29 | 송재익, 김명훈 | 단위테스트케이스(계획) | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
통합 테스트 설계 | 10% |  | 50% | 2021-10-25 | 2021-10-29 | 송재익, 김명훈 | 통합테스트시나리오(계획) | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
검사기준 정의 | 4% |  | 20% | 2021-11-01 | 2021-11-05 | 양승현 | 검사기준서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
구현 | 30% |  |  | 2021-10-25 | 2021-12-03 | 다차원분석 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25% | 0.5% | 0.75% | 1% | 1.5% | 2% | 2.5% | 3% | 3.5% | 4% | 4.5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.075% | 0.15% | 0.225% | 0.3% | 0.45% | 0.6% | 0.75% | 0.9% | 1.05% | 1.2% | 1.35% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5%
응용프로그램 구현 |  | 100% |  | 2021-10-25 | 2021-11-26 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
개발환경 구성 | 5% |  | 5% | 2021-10-25 | 2021-10-25 | 권영호, 양승현 | 개발환경가이드 | [20 empty] | 5% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | [11 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25% | 0.25% | 0.25% | 0.25% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
개발(개발 상세일정을 별도 관리) | 75% |  | 75% | 2021-10-26 | 2021-11-26 | 다차원분석팀 | 소스 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
단위시험 수행 | 20% |  | 20% | 2021-11-01 | 2021-12-03 | 다차원분석팀 | 단위테스트케이스(결과) | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시험 | 23% |  |  | 2021-12-06 | 2021-12-24 | 다차원분석 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 40% | 52% | 67% | 86% | 90% | 90% | 90% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.76% | 9.2% | 11.96% | 15.41% | 19.78% | 20.7% | 20.7% | 20.7% | 20.7%
통합테스트 |  | 40% |  | 2021-12-06 | 2021-12-10 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
통합테스트 수행 | 40% |  | 100% | 2021-12-06 | 2021-12-10 | 우현종, 양승현 | 통합테스트시나리오(결과) | 2021년 35주차 4월3주차 4월16일: 30%; 2021년 36주차 4월4주차 4월23일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 12%; 2021년 36주차 4월4주차 4월23일: 28%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
시스템테스트 |  | 20% |  | 2021-12-13 | 2021-12-17 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시큐어코딩/웹취약점 조치 | 10% |  | 50% | 2021-12-13 | 2021-12-17 | 다차원분석팀 | 시큐어코딩, 웹취약점 점검 및 조치결과서
성능점검결과 조치 | 10% |  | 50% | 2021-12-13 | 2021-12-17 | 다차원분석팀 | 소스 | 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 30%; 2021년 40주차 5월3주차 5월21일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 3%; 2021년 39주차 5월2주차 5월14일: 3%; 2021년 40주차 5월3주차 5월21일: 4%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
사용자테스트 |  | 40% |  | 2021-12-20 | 2021-12-24 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
사용자테스트 수행 | 40% |  | 100% | 2021-12-20 | 2021-12-24 | 우현종, 양승현 | 사용자(승인)테스트결과서 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 12%; 2021년 38주차 5월1주차 5월7일: 12%; 2021년 39주차 5월2주차 5월14일: 16%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
이행 | 7% |  |  | 2021-12-13 | 2021-12-31 | 다차원분석 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 18% | 40% | 70% | 72.7% | 79% | 89.5% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.26% | 2.8% | 4.9% | 5.089% | 5.53% | 6.265% | 7%
이행계획 수립 |  | 20% |  | 2021-12-13 | 2021-12-17 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
이행계획 수립 | 10% |  | 50% | 2021-12-13 | 2021-12-13 | 권영호, 양승현 | 이행계획서(시스템 오픈) | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 3%; 2021년 38주차 5월1주차 5월7일: 7%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
시스템 적용(시스템 오픈) | 10% |  | 50% | 2021-12-14 | 2021-12-17 | 권영호, 양승현 | 이행결과서 | 2021년 39주차 5월2주차 5월14일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 10%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
매뉴얼 작성 |  | 50% |  | 2021-12-20 | 2021-12-24 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
사용자매뉴얼 작성 | 35% |  | 70% | 2021-12-20 | 2021-12-24 | 다차원분석팀 | 사용자매뉴얼 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 10.5%; 2021년 38주차 5월1주차 5월7일: 10.5%; 2021년 39주차 5월2주차 5월14일: 14%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
운영자매뉴얼 작성 | 15% |  | 30% | 2021-12-20 | 2021-12-24 | 다차원분석팀 | 운영자매뉴얼 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 4.5%; 2021년 38주차 5월1주차 5월7일: 4.5%; 2021년 39주차 5월2주차 5월14일: 6%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
인수인계 및 운영 |  | 30% |  | 2021-12-27 | 2021-12-31 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
사용자/운영자 교육훈련 실시 | 9% |  | 30% | 2021-12-27 | 2021-12-31 | 다차원분석팀 | 사용자교육결과서 | 2021년 40주차 5월3주차 5월21일: 30%; 2021년 41주차 5월4주차 5월28일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 2.7%; 2021년 41주차 5월4주차 5월28일: 6.3%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
운영지원 | 21% |  | 70% | 2021-12-27 | 2022-01-31 | 다차원분석팀 |  | 2021년 42주차 6월1주차 6월4일: 50%; 2021년 43주차 6월2주차 6월10일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 10.5%; 2021년 43주차 6월2주차 6월10일: 10.5%

## 통계분석(계획)
공정명 | 중요도 |  |  | 시작예정일 | 종료예정일 | 업무담당 | 산출물 | 2020년 | [18 empty] | 2021년 | [23 empty] | 2020년 | [18 empty] | 2021년
[8 empty] | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차 | 1주차 | 2주차 | 3주차 | 4주차 | 5주차 | 6주차 | 7주차 | 8주차 | 9주차 | 10주차 | 11주차 | 12주차 | 13주차 | 14주차 | 15주차 | 16주차 | 17주차 | 18주차 | 19주차 | 20주차 | 21주차 | 22주차 | 23주차 | 24주차 | 25주차 | 26주차 | 27주차 | 28주차 | 29주차 | 30주차 | 31주차 | 32주차 | 33주차 | 34주차 | 35주차 | 36주차 | 37주차 | 38주차 | 39주차 | 40주차 | 41주차 | 42주차 | 43주차
[8 empty] | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차 | 8월4주차 | 8월5주차 | 9월1주차 | 9월2주차 | 9월3주차 | 9월4주차 | 10월1주차 | 10월2주차 | 10월3주차 | 10월4주차 | 10월5주차 | 11월1주차 | 11월2주차 | 11월3주차 | 11월4주차 | 12월1주차 | 12월2주차 | 12월3주차 | 12월4주차 | 1월1주차 | 1월2주차 | 1월3주차 | 1월4주차 | 1월5주차 | 2월1주차 | 2월2주차 | 2월3주차 | 2월4주차 | 3월1주차 | 3월2주차 | 3월3주차 | 3월4주차 | 4월1주차 | 4월2주차 | 4월3주차 | 4월4주차 | 4월5주차 | 5월1주차 | 5월2주차 | 5월3주차 | 5월4주차 | 6월1주차 | 6월2주차
| Stage | Step | Task |  |  |  |  | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일 | 8월21일 | 8월28일 | 9월4일 | 9월11일 | 9월18일 | 9월25일 | 10월2일 | 10월9일 | 10월 16일 | 10월 23일 | 10월30일 | 11월6일 | 11월13일 | 11월 20일 | 11월27일 | 12월4일 | 12월11일 | 12월18일 | 12월25일 | 1월1일 | 1월8일 | 1월15일 | 1월22일 | 1월29일 | 2월5일 | 2월12일 | 2월19일 | 2월26일 | 3월5일 | 3월12일 | 3월19일 | 3월26일 | 4월2일 | 4월9일 | 4월16일 | 4월23일 | 4월30일 | 5월7일 | 5월14일 | 5월21일 | 5월28일 | 6월4일 | 6월10일
평가 및 교류협력 | [7 empty] | 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 1%; 2020년 7주차 10월1주차 10월2일: 2%; 2020년 8주차 10월2주차 10월9일: 3%; 2020년 9주차 10월3주차 10월 16일: 4%; 2020년 10주차 10월4주차 10월 23일: 4%; 2020년 11주차 10월5주차 10월30일: 4%; 2020년 12주차 11월1주차 11월6일: 4%; 2020년 13주차 11월2주차 11월13일: 4.462%; 2020년 14주차 11월3주차 11월 20일: 5.353%; 2020년 15주차 11월4주차 11월27일: 7.201%; 2020년 16주차 12월1주차 12월4일: 8.29%; 2020년 17주차 12월2주차 12월11일: 8.686%; 2020년 18주차 12월3주차 12월18일: 9.28%; 2020년 19주차 12월4주차 12월25일: 11.19%; 2021년 20주차 1월1주차 1월1일: 15.66%; 2021년 21주차 1월2주차 1월8일: 15.74%; 2021년 22주차 1월3주차 1월15일: 15.81%; 2021년 23주차 1월4주차 1월22일: 15.89%; 2021년 24주차 1월5주차 1월29일: 15.96%; 2021년 25주차 2월1주차 2월5일: 16.11%; 2021년 26주차 2월2주차 2월12일: 16.26%; 2021년 27주차 2월3주차 2월19일: 16.41%; 2021년 28주차 2월4주차 2월26일: 16.56%; 2021년 29주차 3월1주차 3월5일: 16.71%; 2021년 30주차 3월2주차 3월12일: 16.86%; 2021년 31주차 3월3주차 3월19일: 17.01%; 2021년 32주차 3월4주차 3월26일: 17.16%; 2021년 33주차 4월1주차 4월2일: 17.16%; 2021년 34주차 4월2주차 4월9일: 17.16%; 2021년 35주차 4월3주차 4월16일: 19.92%; 2021년 36주차 4월4주차 4월23일: 26.36%; 2021년 37주차 4월5주차 4월30일: 30.9%; 2021년 38주차 5월1주차 5월7일: 36.98%; 2021년 39주차 5월2주차 5월14일: 42.89%; 2021년 40주차 5월3주차 5월21일: 43.9%; 2021년 41주차 5월4주차 5월28일: 44.12%; 2021년 42주차 6월1주차 6월4일: 44.49%; 2021년 43주차 6월2주차 6월10일: 44.86%
요구정의 | 8% |  |  | 2021-09-13 | 2021-10-01 | 통계분석 |  | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 0% | 0% | 0% | 0% | 0% | 0.8% | 1.6% | 2.4% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2% | 3.2%
요구사항정의 |  | 100% |  | 2021-09-13 | 2021-10-01 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
요구사항 정의 | 80% |  | 80% | 2021-09-13 | 2021-09-28 |  | 요구사항정의서 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 20%; 2020년 7주차 10월1주차 10월2일: 20%; 2020년 8주차 10월2주차 10월9일: 20%; 2020년 9주차 10월3주차 10월 16일: 20%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
요구사항 확정 | 20% |  | 20% | 2021-09-29 | 2021-10-01 |  | 요구사항정의서 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 5%; 2020년 7주차 10월1주차 10월2일: 5%; 2020년 8주차 10월2주차 10월9일: 5%; 2020년 9주차 10월3주차 10월 16일: 5%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
분석 | 10% |  |  | 2021-10-04 | 2021-10-15 | 통계분석 |  | 0% | 0% | 0% | 0% | 0% | 10% | 20% | 30% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 40% | 0% | 0% | 0% | 0% | 0% | 1% | 2% | 3% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4% | 4%
업무 분석 |  | 40% |  | 2021-10-04 | 2021-10-08 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
업무 절차 분석 | 40% |  | 100% | 2021-10-04 | 2021-10-08 |  | 업무흐름도 | 2020년 6주차 9월4주차 9월25일: 25%; 2020년 7주차 10월1주차 10월2일: 25%; 2020년 8주차 10월2주차 10월9일: 25%; 2020년 9주차 10월3주차 10월 16일: 25%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 10%; 2020년 7주차 10월1주차 10월2일: 10%; 2020년 8주차 10월2주차 10월9일: 10%; 2020년 9주차 10월3주차 10월 16일: 10%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
데이터 분석 |  | 50% |  | 2021-10-11 | 2021-10-15 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
논리데이터 모델링 | 50% |  | 100% | 2021-10-11 | 2021-10-15 |  | 논리-ERD | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
UI 분석 |  | 10% |  | 2021-10-11 | 2021-10-15 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
메뉴구성도 | 10% |  | 100% | 2021-10-11 | 2021-10-15 |  | 메뉴구성도 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
설계 | 22% |  |  | 2021-10-18 | 2021-01-01 | 통계분석 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.1% | 6.15% | 14.55% | 19.5% | 21.3% | 24% | 32.7% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 53% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.462% | 1.353% | 3.201% | 4.29% | 4.686% | 5.28% | 7.194% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66% | 11.66%
시스템 구조 설계 |  | 15% |  | 2021-10-18 | 2021-10-20 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
아키텍처 설계 | 10.5% |  | 70% | 2021-10-18 | 2021-10-20 |  | 아키텍처정의서 | 2020년 13주차 11월2주차 11월13일: 20%; 2020년 14주차 11월3주차 11월 20일: 30%; 2020년 15주차 11월4주차 11월27일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 2.1%; 2020년 14주차 11월3주차 11월 20일: 3.15%; 2020년 15주차 11월4주차 11월27일: 5.25%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
개발표준정의 | 4.5% |  | 30% | 2021-10-21 | 2021-10-22 |  | 개발표준정의정의서 | 2020년 15주차 11월4주차 11월27일: 30%; 2020년 16주차 12월1주차 12월4일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 1.35%; 2020년 16주차 12월1주차 12월4일: 3.15%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
데이터 설계 |  | 15% |  | 2021-10-25 | 2021-10-29 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
물리 데이터 모델링 | 9% |  | 60% | 2021-10-25 | 2021-10-29 |  | 물리-ERD | 2020년 14주차 11월3주차 11월 20일: 10%; 2020년 15주차 11월4주차 11월27일: 20%; 2020년 16주차 12월1주차 12월4일: 20%; 2020년 17주차 12월2주차 12월11일: 20%; 2020년 18주차 12월3주차 12월18일: 30%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0.9%; 2020년 15주차 11월4주차 11월27일: 1.8%; 2020년 16주차 12월1주차 12월4일: 1.8%; 2020년 17주차 12월2주차 12월11일: 1.8%; 2020년 18주차 12월3주차 12월18일: 2.7%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
테이블/코드설계 | 6% |  | 40% | 2021-10-25 | 2021-10-29 |  | 테이블정의서, 코드정의서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
데이터 수집 설계 |  | 20% |  | 2021-12-14 | 2021-01-01 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
ETL 정의 | 12% |  | 60% | 2021-12-21 | 2021-01-01 |  | ETL 정의서 | 2020년 19주차 12월4주차 12월25일: 30%; 2021년 20주차 1월1주차 1월1일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 3.6%; 2021년 20주차 1월1주차 1월1일: 8.4%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
WorkFlow 정의 | 8% |  | 40% | 2021-12-21 | 2021-01-01 |  | WorkFlow 정의서 | 2020년 19주차 12월4주차 12월25일: 30%; 2021년 20주차 1월1주차 1월1일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 2.4%; 2021년 20주차 1월1주차 1월1일: 5.6%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
프로그램 설계 |  | 30% |  | 2021-10-18 | 2021-10-29 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
프로그램 설계 | 9% |  | 30% | 2021-10-18 | 2021-10-22 |  | 프로그램목록/설계서 | 2020년 19주차 12월4주차 12월25일: 30%; 2021년 20주차 1월1주차 1월1일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 2.7%; 2021년 20주차 1월1주차 1월1일: 6.3%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
화면설계 | 15% |  | 50% | 2021-10-21 | 2021-10-22 |  | 화면목록/설계서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
인터페이스 설계 | 6% |  | 20% | 2021-10-25 | 2021-10-29 |  | 인터페이스목록/정의서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시험 설계 |  | 20% |  | 2021-10-25 | 2021-10-29 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
단위테스트 설계 | 6% |  | 30% | 2021-10-25 | 2021-10-29 |  | 단위테스트케이스(계획) | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
통합 테스트 설계 | 10% |  | 50% | 2021-10-25 | 2021-10-29 |  | 통합테스트시나리오(계획) | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
검사기준 정의 | 4% |  | 20% | 2021-11-01 | 2021-11-05 |  | 검사기준서 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
구현 | 30% |  |  | 2021-10-25 | 2021-12-03 | 통계분석 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25% | 0.5% | 0.75% | 1% | 1.5% | 2% | 2.5% | 3% | 3.5% | 4% | 4.5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.075% | 0.15% | 0.225% | 0.3% | 0.45% | 0.6% | 0.75% | 0.9% | 1.05% | 1.2% | 1.35% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5% | 1.5%
응용프로그램 구현 |  | 100% |  | 2021-10-25 | 2021-11-26 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
개발환경 구성 | 5% |  | 5% | 2021-10-25 | 2021-10-25 |  | 개발환경가이드 | [20 empty] | 5% | 5% | 5% | 5% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | 10% | [11 empty] | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0.25% | 0.25% | 0.25% | 0.25% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0.5% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
개발(개발 상세일정을 별도 관리) | 75% |  | 75% | 2021-10-26 | 2021-11-26 |  | 소스 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
단위시험 수행 | 20% |  | 20% | 2021-11-01 | 2021-12-03 |  | 단위테스트케이스(결과) | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시험 | 23% |  |  | 2021-12-06 | 2021-12-24 | 통계분석 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 12% | 40% | 52% | 67% | 86% | 90% | 90% | 90% | 90% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 2.76% | 9.2% | 11.96% | 15.41% | 19.78% | 20.7% | 20.7% | 20.7% | 20.7%
통합테스트 |  | 40% |  | 2021-12-06 | 2021-12-10 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
통합테스트 수행 | 40% |  | 100% | 2021-12-06 | 2021-12-10 |  | 통합테스트시나리오(결과) | 2021년 35주차 4월3주차 4월16일: 30%; 2021년 36주차 4월4주차 4월23일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 12%; 2021년 36주차 4월4주차 4월23일: 28%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
시스템테스트 |  | 20% |  | 2021-12-13 | 2021-12-17 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
시큐어코딩/웹취약점 조치 | 10% |  | 50% | 2021-12-13 | 2021-12-17 |  | 시큐어코딩, 웹취약점 점검 및 조치결과서
성능점검결과 조치 | 10% |  | 50% | 2021-12-13 | 2021-12-17 |  | 소스 | 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 30%; 2021년 40주차 5월3주차 5월21일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 3%; 2021년 39주차 5월2주차 5월14일: 3%; 2021년 40주차 5월3주차 5월21일: 4%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
사용자테스트 |  | 40% |  | 2021-12-20 | 2021-12-24 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
사용자테스트 수행 | 40% |  | 100% | 2021-12-20 | 2021-12-24 |  | 사용자(승인)테스트결과서 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 12%; 2021년 38주차 5월1주차 5월7일: 12%; 2021년 39주차 5월2주차 5월14일: 16%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
이행 | 7% |  |  | 2021-12-13 | 2021-12-31 | 통계분석 |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 25.5% | 63% | 85% | 86.35% | 89.5% | 94.75% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 1.785% | 4.41% | 5.95% | 6.044% | 6.265% | 6.632% | 7%
이행계획 수립 |  | 30% |  | 2021-12-13 | 2021-12-17 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
이행계획 수립 | 30% |  | 100% | 2021-12-13 | 2021-12-13 |  | 이행계획서(시스템 오픈) | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 9%; 2021년 38주차 5월1주차 5월7일: 21%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
시스템 적용(시스템 오픈) |  |  |  | 2021-12-14 | 2021-12-17 |  | 이행결과서 | 2021년 39주차 5월2주차 5월14일: 100%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
매뉴얼 작성 |  | 55% |  | 2021-12-20 | 2021-12-24 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
사용자매뉴얼 작성 | 38.5% |  | 70% | 2021-12-20 | 2021-12-24 |  | 사용자매뉴얼 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 11.55%; 2021년 38주차 5월1주차 5월7일: 11.55%; 2021년 39주차 5월2주차 5월14일: 15.4%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
운영자매뉴얼 작성 | 16.5% |  | 30% | 2021-12-20 | 2021-12-24 |  | 운영자매뉴얼 | 2021년 37주차 4월5주차 4월30일: 30%; 2021년 38주차 5월1주차 5월7일: 30%; 2021년 39주차 5월2주차 5월14일: 40%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 4.95%; 2021년 38주차 5월1주차 5월7일: 4.95%; 2021년 39주차 5월2주차 5월14일: 6.6%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
인수인계 및 운영 |  | 15% |  | 2021-12-27 | 2021-12-31 | bar: 2020년 1주차 8월4주차 8월21일 to 2021년 43주차 6월2주차 6월10일
사용자/운영자 교육훈련 실시 | 4.5% |  | 30% | 2021-12-27 | 2021-12-31 |  | 사용자교육결과서 | 2021년 40주차 5월3주차 5월21일: 30%; 2021년 41주차 5월4주차 5월28일: 70%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 1.35%; 2021년 41주차 5월4주차 5월28일: 3.15%; 2021년 42주차 6월1주차 6월4일: 0%; 2021년 43주차 6월2주차 6월10일: 0%
운영지원 | 10.5% |  | 70% | 2021-12-27 | 2022-01-31 |  |  | 2021년 42주차 6월1주차 6월4일: 50%; 2021년 43주차 6월2주차 6월10일: 50%; 2020년 1주차 8월4주차 8월21일: 0%; 2020년 2주차 8월5주차 8월28일: 0%; 2020년 3주차 9월1주차 9월4일: 0%; 2020년 4주차 9월2주차 9월11일: 0%; 2020년 5주차 9월3주차 9월18일: 0%; 2020년 6주차 9월4주차 9월25일: 0%; 2020년 7주차 10월1주차 10월2일: 0%; 2020년 8주차 10월2주차 10월9일: 0%; 2020년 9주차 10월3주차 10월 16일: 0%; 2020년 10주차 10월4주차 10월 23일: 0%; 2020년 11주차 10월5주차 10월30일: 0%; 2020년 12주차 11월1주차 11월6일: 0%; 2020년 13주차 11월2주차 11월13일: 0%; 2020년 14주차 11월3주차 11월 20일: 0%; 2020년 15주차 11월4주차 11월27일: 0%; 2020년 16주차 12월1주차 12월4일: 0%; 2020년 17주차 12월2주차 12월11일: 0%; 2020년 18주차 12월3주차 12월18일: 0%; 2020년 19주차 12월4주차 12월25일: 0%; 2021년 20주차 1월1주차 1월1일: 0%; 2021년 21주차 1월2주차 1월8일: 0%; 2021년 22주차 1월3주차 1월15일: 0%; 2021년 23주차 1월4주차 1월22일: 0%; 2021년 24주차 1월5주차 1월29일: 0%; 2021년 25주차 2월1주차 2월5일: 0%; 2021년 26주차 2월2주차 2월12일: 0%; 2021년 27주차 2월3주차 2월19일: 0%; 2021년 28주차 2월4주차 2월26일: 0%; 2021년 29주차 3월1주차 3월5일: 0%; 2021년 30주차 3월2주차 3월12일: 0%; 2021년 31주차 3월3주차 3월19일: 0%; 2021년 32주차 3월4주차 3월26일: 0%; 2021년 33주차 4월1주차 4월2일: 0%; 2021년 34주차 4월2주차 4월9일: 0%; 2021년 35주차 4월3주차 4월16일: 0%; 2021년 36주차 4월4주차 4월23일: 0%; 2021년 37주차 4월5주차 4월30일: 0%; 2021년 38주차 5월1주차 5월7일: 0%; 2021년 39주차 5월2주차 5월14일: 0%; 2021년 40주차 5월3주차 5월21일: 0%; 2021년 41주차 5월4주차 5월28일: 0%; 2021년 42주차 6월1주차 6월4일: 5.25%; 2021년 43주차 6월2주차 6월10일: 5.25%